AT Network Quarterly Report

Reporting Period: January 1, 2014 – March 31, 2014

(Year 2, Quarter Three)

Contract # 28634

Submitted by

California Foundation for Independent Living Centers

Table of Contents

Press Ctrl + Click on any of the section titles below to jump to that section.

Statewide Leadership Activities	1

I.	TRAININGS & EVENTS	1

II.	TECHNICAL ASSISTANCE (TA)	4

III.	PUBLIC AWARENESS	6

A.	Outreach & Public Awareness Events	6

B.	Outreach and Under-represented populations	6

C.	Social Media	6

E.	AT Network Information & Referral	8

IV.	COORDINATION & COLLABORATION	8

State Level Activities	10

I.	DEVICE LOAN PROGRAM	10

II.	AT REUTILIZATION	14

A.	California AT Reuse Coalition (CATRC)	14

B.	Reuse Best Practice Sessions	14

C.	Statewide Device Refurbishment/Repair/Recycle Activities	14

III.	STATE FINANCING ACTIVITIES	16

Introduction

This report covers January through March 2014 and is divided into two sections: Statewide Leadership Activities and State Level Activities. Each area is further subdivided into program areas.

# Statewide Leadership Activities

## TRAININGS & EVENTS

- Annual Training Deliverable Overview

| Contract year July 1, 2013 – June 30, 2014 | AT 101 (Basics) | AT In-Depth | AT Quarterly In-Person meetings |
| --- | --- | --- | --- |
| Annual Contract Obligation | 4 | 6 | 8 4 in the North 4 in the South |
| Quarter 1 (July – Sept) | 0 | 1 | 3 (2 North; 1 South) |
| Quarter 2 (Oct – Dec) | 1 | 2 | 2 |
| Quarter 3 (Jan – March) | 1 | 1 | 2 |

- AT Webinars

During this reporting period, the AT Network hosted two AT Webinars. One webinar was part of our AT 101 series and one webinar was part of our AT In-Depth series. All webinar trainings were captioned and posted on the AT Network website, including a YouTube version on the AT Network’s YouTube channel.

We also hosted a webinar in early January that we are not including in our statistics or description due to the myriad of technical issues we encountered during the webinar due to our webinar company’s server migration. A repeat webinar on AT Evaluation has been rescheduled for June 2014.

- Training Tier One: AT 101 Basics

AT & the IEP (Individualized Education Program) on March 11, 2014

Participants learned about parent and student rights, resolving disputes, and how to effectively communicate with their school team members during an Individualized Education Program (IEP) process.

Fourteen participants attended the webinar training. Four participants responded to the webinar survey. 75% found the training to be very relevant.

- Training Tier Two: AT In-Depth Training

An Overview of Section 504 & Public School Responsibilities (K-12) on February 6, 2014

Participants learned about the public schools' responsibilities, Section 504 Evaluation, 504 Plans & Services, and Procedural Safeguards.

Twenty participants attended the webinar training.  Seven participants responded to the webinar evaluation.  86% of webinar respondents found the training to be very relevant.

- AT Network Regional In-Person Meetings/Trainings

During this reporting period, the AT Network hosted two AT Network Regional In-Person Meetings.

During this reporting period, the AT Network hosted two AT Network Regional In-Person Meetings.

The Southern Regional In-Person Meeting was held on February 20, 2014 at the Molina Healthcare of California, Long Beach, CA.  Participants received two informative presentations.

- Randyce Wetcher & Michael Wetcher, presented on Adaptive Voice's software, CDesk.  Participants learned a stand-alone, all-inclusive software program for blind, low-vision, seniors and individuals with physical disabilities that enables access to the most commonly used functions of their computers.

- Lisa Hayes, Director of Disability & Senior Access Services, presented Molina Healthcare's services, Seniors and Persons with disabilities members, current healthcare, its collaborators, as well as their accessible clinics.

Twenty people attended the in-person meeting.  Fourteen participants responded to the evaluation.  The majority of the participants indicated the presentations were very informative and valuable. Participants enjoyed learning about how CDesk is a single screen reader and screen magnification program with over 21 applications that is simple to use as well as easy to learn.  In addition, participants learned Lisa Hayes' experience in the healthcare and AT and how we can work together.

The Northern Regional In-Person Meeting was held on Thursday, March 20th at Contra Costa College in San Pablo, CA.  25 people attended. Lunch was sponsored by WHILL, Inc.  Participants received a brief presentation on the DSPS services at Contra Costa College and then two in-depth presentations.

- Hazel Watson of the Communication Technology Education Center (CTEC) in Sacramento presented on a wide variety of options for communication, including AAC devices.  She brought examples and explained CTEC’s evaluation methods.

- WHILL, Inc shared their prototype of a unique wheelchair that they refer to as a mobility device.  The CEO, Mr. Sugie presented the inspiration for their mobility device and then let people take it for a ride outside.

Eleven participants completed the evaluations. The feedback was all positive. They were impressed with both presentations and also liked that   lunch was provided by a sponsor.  One person wrote, “The fact that Hazel was so knowledgeable and open to all questions really made me feel like I made a friend in the AAC world and will be able to ask her my questions that come up.  Also, getting to see the WHILL in action made me realize how important it is for wheelchairs users to have pride in their equipment, and I loved that people could test ride it. Also, lunch was excellent but we needed a little more food. ” Scores were all 4-5 and positive evaluations and comments all around.

- ILC-based AT Advocates Orientations to the AT Network

- The AT Network provided an AT Advocate Orientation on March 5th. The orientation provides information to new AT Advocates about the AB 204 requirements for ILCs, AT Network’s services, technical assistance provided to Independent Living Centers and ways that AT Advocates can collaborate with the hub. Seven AT Advocates attended the training representing the ILCs in Bakersfield, Concord, Garden Grove, Marin, Nevada City, Redding and San Diego.

- AT Network Channel on YouTube

During this reporting period, the AT Network posted two videos to the AT Network’s YouTube Channel.

- An Overview of Section 504 & Public School Responsibilities (K-12); and

- Assistive Technology & the IEP (Individualized Education Program).

- Training and Webinar Event Totals

During this reporting period 86 people received direct training from the AT Network hub. This total does not include the people who receive training from

## TECHNICAL ASSISTANCE (TA)

- Independent Living Centers and AT Advocates

  - ILC-based AT Advocates Monthly Webinar Meetings

During this reporting period the AT Network hosted three AT Advocates meetings. All meetings focused on specific training needs and collaboration opportunities for AT Advocates. The webinar meetings were facilitated by CFILC.

- January 8, 2014 (13 attendees)

- February 13, 2014 (13 attendees)

- March 13, 2014 (11 attendees)

- Device Lending Libraries (DLLs)

New DLL staff received training and assistance with the AT Exchange. In addition, all DLL staff received TA and training on reporting requirements to meet contract deliverables.

- AT Advocates Online Community

CFILC continues to maintain a password protected website where AT Advocates can log in and have access to the following resources: contact information of AT Advocates throughout California, including their areas of expertise, recordings of the AT Advocates’ monthly webinar meetings, and the online AT Network outreach efforts reporting form. During this reporting period the AT Advocates user profiles were updated and new advocates were added.

- AT Network Membership

At the end of March 2014, the AT Network membership totaled 399.

- Reuse Centers

CFILC staff continued to provide technical assistance to the 4 contracted reuse centers on the AT Exchange. In addition, the Keep the Wheels Rolling Repair Fund remained available to reuse centers throughout California and CFILC staff provided technical assistance to new reuse centers accessing funds to ensure that their organization was entered on the exchange and the equipment properly posted.

## PUBLIC AWARENESS

### Outreach & Public Awareness Events

During this reporting period, the AT Network conducted 94 public awareness events, including 51 presentations/demonstrations, 39 outreach events and 3 mailings.

The AT Network distributed 4,030 materials including 2,395 materials in English, 221 outreach materials in Spanish, 81 outreach materials in Chinese and 1,333 marketing and promotional items.

### Outreach and Under-represented populations

The AT Network has identified the following populations as underserved throughout the state: Youth with disabilities and their families, Latinos with disabilities and their families, Seniors with disabilities and their families.

During this reporting period the AT Network conducted 15 events focused on Seniors with Disabilities and their families, 7 events focused on  Youth with Disabilities and their families, and 2 events focused on Latinos with Disabilities and their families.

### Social Media

AT Blog

During this reporting period 11 blog posts were written and 12 comments were made. The blog currently has a total of 117 subscribers. The AT Blog received an average of 4,355 page views per month during this reporting period.

Facebook

The AT Network’s Facebook page received 53 new likes this quarter. Our Facebook page had a total of 367 likes at the end of the quarter. AT staff is averaging 10 posts each week.

Instagram

We began publicizing the Instagram account by including an icon on our AT Network homepage. We currently have 25 followers.

Twitter

The AT Network added 14 new Twitter followers this quarter. We currently have 170  followers and average 3.5  tweets per week.

- AT Network Website

During this quarter there were a total of 10,594 visitors to the AT Network website. 10,594 were unique visits.  73.4% of all visitors were new to the site.  The website received a total of 30,902 page views.

### AT Network Information & Referral

The AT Network Information and Referral service answered 231 inquiries (calls and emails) during this reporting period. 76 (33.3%) were calls about AT devices or services; 67 people (29%) inquired about AT funding; and 88 (38%) of questions were about other disability related topics.

| Role Of Caller | AT Devices/ Services | AT Funding | Other topics | TOTALS |
| --- | --- | --- | --- | --- |
| People with Disabilities | 18 | 31 | 39 | 88 |
| Family, Guardian, Authorized rep | 7 | 20 | 11 | 38 |
| Rep of education | 9 | 0 | 2 | 11 |
| Rep of employment | 1 | 0 | 0 | 1 |
| Rep of health, allied health, rehab | 8 | 1 | 4 | 13 |
| Rep of community living | 5 | 4 | 1 | 10 |
| Rep of technology | 1 | 0 | 0 | 1 |
| other | 27 | 11 | 31 | 69 |
| Total | 76 | 67 | 88 | 231 |

In the first quarter of this year the AT Network received 235 I&R inquiries. In the second quarter we received 177 inquiries. Combining all three quarters, we have received a total of 643 I&R inquiries this contract year.

## COORDINATION & COLLABORATION

- AT Network listserv for ILC Directors and AT Announcements

The AT Network continued to provide announcements to the ILC Directors and AT Announcements listservs.

- Organizational Collaboration

- CFILC continued to partner with the California Emerging Technology Fund to promote the availability of low-cost/no-cost Internet to people with disabilities by maintaining a link to the promotion on the AT Network website and emailing information about the program to our networks.

- During this reporting period CFILC continued to participate in the Sacramento MIND Institute’s AT Consortium by attending meetings and participating in the planning of local presentations and resource fairs.

- In December the AT Network’s Program Director joined the California Braille and Teach listserv that exists to connect educators working with students with vision impairments. Since that time the AT Network has been able to serve listserv members by loaning devices like CCTVs and portable magnifiers to individuals for trial periods or while waiting for funding approval for a school district to purchase a device.

- CFILC continued our collaboration with Batteries Plus retailers across California to offer discounts on batteries to our partner reuse organizations.

# State Level Activities

## DEVICE LOAN PROGRAM

The current contract for the 14 current device lending libraries covers the period from July 1, 2013 through June 30, 2014. Included in the contract are performance standards for outreach/marketing and device loan.

  - Number Of Short-Term Loans By Primary Purpose Of Loan

As shown in the table below, the 14 centers participating in the Device Lending Library (DLL) program made 378 short-term device loans during this quarter in four purpose categories. Of these loans, 274 were made to help the recipient make a decision (device trial or evaluation), 45 devices served as loaners during a device repair period or while waiting for funding to purchase a device, 47 were intended to provide an accommodation on a short-term basis, and 12 were for other purposes.

| DLL | Assist in Decision Making | Serve as Loaner | Provide Short-Term Accommodation | Other | TOTAL |
| --- | --- | --- | --- | --- | --- |
| ATEC | 18 | 6 | 1 |  | 25 |
| CART | 23 | 1 |  |  | 24 |
| CCATC | 35 | 5 | 1 |  | 41 |
| CCCIL | 18 | 5 |  |  | 23 |
| CRIL | 12 | 1 | 1 |  | 14 |
| FREED | 12 | 1 | 21 |  | 34 |
| ILRCSF | 7 | 1 | 3 |  | 11 |
| ILSNC | 4 | 7 | 3 |  | 14 |
| KATC | 33 | 5 | 1 | 1 | 40 |
| ROLLING START | 22 | 1 | 7 |  | 30 |
| SDATC | 34 | 7 |  | 10 | 51 |
| SVILC | 13 | 2 | 9 | 1 | 25 |
| TCILC | 27 | 3 |  |  | 30 |
| UCP SJ | 16 |  |  |  | 16 |
| TOTAL | 274 | 45 | 47 | 12 | 378 |

B. Number Of Device Loans By Type Of Borrower

| DLL | Individual w/ Disability | Family, Guardian | Education | Employment | Health, Rehab | Comm. Living | Tech | Other | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ATEC | 8 | 15 | 1 |  | 1 |  |  |  | 25 |
| CART |  | 21 |  |  | 3 |  |  |  | 24 |
| CCATC | 16 | 11 | 7 |  | 5 | 2 |  |  | 41 |
| CCCIL | 17 | 5 |  |  |  | 1 |  |  | 23 |
| CRIL | 9 | 2 | 1 |  |  | 1 | 1 |  | 14 |
| FREED | 21 | 9 | 1 |  | 1 |  |  | 2 | 34 |
| ILRCSF | 6 | 3 |  |  | 1 |  |  | 1 | 11 |
| ILSNC | 9 | 4 |  |  | 3 |  |  |  | 16 |
| KATC | 7 | 19 | 13 |  |  | 1 |  |  | 40 |
| RSI | 18 | 2 | 8 |  |  | 2 |  |  | 30 |
| SDATC | 9 | 21 | 13 |  | 5 |  | 3 |  | 51 |
| SVILC | 15 | 6 |  |  | 1 |  | 3 |  | 25 |
| TCILC | 23 | 5 |  |  |  |  |  |  | 28 |
| UCPSJ |  | 2 |  |  |  |  | 14 |  | 16 |
|  | 158 | 125 | 44 |  | 20 | 7 | 21 | 3 | 378 |

C.  Length Of AT Device Loans

All AT Device Loans are issued for 30 days and are extended if requested by the recipient and if no one is waiting for the device.

  - Types Of Devices Loaned

Type of Device      		TOTAL

| Type of Device | Total |
| --- | --- |
| Computers & Related | 136 |
| Daily Living | 27 |
| Environmental Adaptions | 13 |
| Hearing | 32 |
| Learning, Cognition & Development | 26 |
| Mobility, Seating and Positioning | 52 |
| None Selected | 0 |
| Other | 13 |
| Recreation, Sports and Leisure | 5 |
| Speech Communication | 106 |
| Vehicle Modification & Transportation | 0 |
| Vision | 61 |
| Total | 471 |

- Consumer Anecdote

An individual had to undergo multiple surgeries and borrowed an 8-foot ramp and a 6-foot ramp so he was able to get in and out of his house. After having the ramps for a few months, his wife purchased a ramp because it was really beneficial for her husband.

## AT REUTILIZATION

### California AT Reuse Coalition (CATRC)

In October, the CATRC Executive Committee strategized an outreach plan to increase coalition membership.  They discussed which organizations to contact and the best approach to reach out to them.  Each committee member was assigned to contact reuse programs closest to their location.  In addition, each committee member decided to take turns facilitating the meetings.  They restructured the agenda to allow general members to share membership announcements, challenges, and success stories.

### Reuse Best Practice Sessions

There were some changes to the AT Reuse Best Practice Sessions.  During this quarter, the CATRC incorporated the AT Reuse Best Practice Session into their regularly scheduled coalition meeting.

Lauren Wetzler from ATEC led the session and nine people attended. The topic was “Diversifying DME donations.” The coalition members shared best practices and suggested looking at Craigslist, contacting independent living centers, healthcare providers, and local hospitals for more donations of different types of equipment.

On November 5th, the Fundraising 101 session was presented by Matt Kamin, the interim Director of Convalescent Aid Society (CAS). CAS is one of the biggest reuse centers in Southern California. Although the focus was on reuse programs, the session was open to all organizations, and we promoted the session as an AT Network training because the topic was applicable to many organizations. The session goal was to provide an open forum for individuals and organizations engaging in reuse, or thinking of starting a program, to exchange ideas and experiences.

### Statewide Device Refurbishment/Repair/Recycle Activities

- Contracted Reuse Organizations

Four reuse programs are contracted to enter and maintain their inventory of used devices for free/sale on the statewide AT Exchange. In addition, they are required to enter all reuse transactions in the AT Exchange database. This arrangement also gives the reuse centers the use of an established online database and builds awareness of their programs. The four participating reuse programs are:

- Center for Independence of Individuals with Disabilities (San Mateo)

- Center for Independent Living (Berkeley)

- Communities Actively Living Independent and Free (CALIF)

- Independent Living Services of Northern California (ILSNC)

- Keep the Wheels Rolling Repair Fund

In October CFILC received a $1,000 grant from CDFI to re-establish the AT Reuse and Repair Fund. The Repair Fund was renamed to Keep the Wheels Rolling Repair Fund (KWRF).  In addition, the AT Network allocated $2,000 to the KWRF. In December, Anthem Blue Cross also donated $5,000 to the Keep the Wheels Rolling Repair Fund bringing the KWRF total to $8,000.

The KWRF fund exists to provide financial assistance to nonprofit reuse centers to repair donated wheelchairs so they can be distributed FREE to community members who need them. Beginning in November 2013, nonprofit organizations engaging in reuse were able to apply for up to $300 each month to repair a wheelchair or scooter. Once the Program Coordinator approves the application, the organization repairs the device and posts it for free on the AT Exchange.  These stipulations ensure that the devices are distributed to new individuals for free and allow the AT Network to collect data for federal reporting and to support future reuse efforts.

- Reuse Totals

The table below breaks down refurbishment/repair/recycle activities in the AT Exchange during this reporting period. It includes activity from contracted reuse centers as well as organizations that received funding from the Keep the Wheels Rolling Repair Fund.

| Type of AT Device | Number of Devices Recycled / Refurbished / Repaired | Total Estimated Current Purchase Price | Total Price for Which Device (s) Were Sold |
| --- | --- | --- | --- |
| Vision | 6 | $3,608 | 0 |
| Hearing | 0 | 0 | 0 |
| Speech Communication | 0 | 0 | 0 |
| Learning, Cognition, and Developmental | 0 | 0 | 0 |
| Mobility, Seating, and Positioning | 78 | $56,380 | $2,670 |
| Daily Living | 42 | $1,808 | $20 |
| Environmental Adaptations | 4 | $74 | 0 |
| Vehicle Modification and Transportation | 1 | $5,000 | 0 |
| Computers and Related | 1 | $130 | 0 |
| Recreation, Sports, and Leisure | 0 | 0 | 0 |
| Other | 3 | $1566 | $500 |
| None Selected | 0 | 0 | 0 |
| Total | 135 | $68,656 | $3,190 |

The total savings to consumers participating in Statewide Reuse Activities during this quarter was $65,466.

A total of 282 devices were distributed this contract year with a savings to consumers of $93,422.

## STATE FINANCING ACTIVITIES

In Fall 2012 CFILC received funding from RSA to create an Alternative Financing Program (AFP) that CFILC titled the FreedomTech Low-Interest Loan Program (FT). This is a separate program from DOR’s AT Loan Guarantee Program (LGP). DOR is responsible for securing a lender for the LGP. CFILC is responsible for securing a lender for the FT program.

During this reporting period CFILC continued to work with Access to Independence (a2i), an ILC in San Diego, toward becoming an authorized lender in California. The goal is for a2i to become one of the FT program’s lenders.

In November, CFILC’s Executive Director attended a funding innovations in AT meeting held in conjunction with the National Disability Institute and Wall Street Without Walls in Washington DC that brought together organizations interested in increasing access to credit for people with disabilities to purchase the assistive technology they need. Many organizational connections were made during the meeting and CFILC deepened our relationship with the National Cooperative Bank (NCB).